## Data
Mortgage
Sprint | Planned Stories | Actual Completed | Cum Planned | Cum Actual | Planned Remaining | Actual Remaining | Ideal Remaining | Delta vs Ideal | Delta vs Plan | Scope
Sprint 1 | 12 | 9 | 12 | 9 | 11 | 14 | 19.7143 | -5.7143 | 3 | 23
Sprint 2 | 4 | 4 | 16 | 13 | 7 | 10 | 16.4286 | -6.4286 | 3 | 23
Sprint 3 | 0 | 0 | 16 | 13 | 7 | 10 | 13.1429 | -3.1429 | 3 | 23
Sprint 4 | 3 | 3 | 19 | 16 | 4 | 7 | 9.8571 | -2.8571 | 3 | 23
Sprint 5 | 6 | 3 | 25 | 19 | 5 | 8 | 6.5714 | 1.4286 | 3 | 30
Sprint 6 | 2 | 0 | 27 | 19 | 3 | 4 | 3.2857 | 0.71429 | 1 | 30
Sprint 7 | 3 | 0 | 30 | 19 | 0 | 4 | 0 | 4 | 4 | 30
InBranch
Sprint | Planned Stories | Actual Completed | Cum Planned | Cum Actual | Planned Remaining | Actual Remaining | Ideal Remaining | Delta vs Ideal | Delta vs Plan | Scope
Sprint 1 | 1 | 1 | 1 | 1 | 12 | 12 | 19.7143 | -7.7143 | 0 | 13
Sprint 2 | 8 | 2 | 9 | 3 | 4 | 10 | 16.4286 | -6.4286 | 6 | 13
Sprint 3 | 4 | 0 | 13 | 3 | 0 | 10 | 13.1429 | -3.1429 | 10 | 13
Payment Switch
Sprint | Planned Points | Actual Completed | Cum Planned | Cum Actual | Planned Remaining | Actual Remaining | Ideal Remaining | Delta vs Ideal | Delta vs Plan | Scope
Sprint 1 | 36 | 36 | 36 | 36 | 86 | 86 | 19.7143 | 66.2857 | 0 | 122
Sprint 2 | 45 | 37 | 81 | 73 | 41 | 49 | 16.4286 | 32.5714 | 8 | 122
Sprint 3 | 28 | 0 | 109 | 73 | 13 | 49 | 13.1429 | 35.8571 | 36 | 122
Sprint 4 | 13 | 0 | 122 | 73 | 0 | 49 | 9.8571 | 39.1429 | 49 | 122
Prod Support -March19 Release
Sprint | Planned Tickets | Actual Completed | Cum Planned | Cum Actual | Planned Remaining | Actual Remaining | Ideal Remaining | Delta vs Ideal | Delta vs Plan | Scope
Sprint 1 | 4 | 4 | 4 | 4 | 23 | 23 | 19.7143 | 3.2857 | 0 | 27
Sprint 2 | 6 | 6 | 10 | 10 | 21 | 21 | 16.4286 | 4.5714 | 0 | 31
Sprint 3 | 20 | 20 | 30 | 30 | 0 | 0 | 13.1429 | -13.1429 | 0 | 30

## Burndown
Sprint Burndown
Notes
Delta vs Ideal > 0: behind ideal (above line)
Delta vs Ideal < 0: ahead of ideal (below line)