## Slide 1: Regression Automation Roadmap
CR9 Retrospective & Full CR Plan – starting Sprint 44 (Sep 23, 2025)

## Slide 2: Assumptions & Constraints
Sprints: 2 weeks. Sprint 44 starts Sep 23, 2025.
CR9 completed May–Aug 2025. Next CRs: 32,6,24,25,29,11 then rest by volume.
KT: 30 minutes (~0.5 team-day) before each new CR.
Include ~20% effort for test case creation before automation.
Maintenance: 0.5 day reserved each Friday; App downtime: Oct 21 & Nov 18, 2025.
US Holidays (2025): Oct 13, Nov 11, Nov 27–28, Dec 25.
Planned sick days: MJ Oct 7; Mohammed Nov 5; Vizarat Dec 9.

## Slide 3: CR Inventory (Sample)
CR Related | Count
Grand Total | 2938
9 | 1071
33 | 375
32 | 314
6 | 232
31 | 161
36 | 107
Print Blank Forms | 71
10 | 70
39 | 62

## Slide 4: Sprint Plan (Next 6 Sprints)
Sprint | Assignments | Total TCs | MJ TCs | Mohammed TCs | Vizarat TCs
Sprint 44 (Sep 23–Oct 06) | CR32:86 | 86 | 20.0 | 33.0 | 33.0
Sprint 45 (Oct 07–Oct 20) | CR32:66 | 66 | 15.0 | 26.0 | 25.0
Sprint 46 (Oct 21–Nov 03) | CR32:76 | 76 | 18.0 | 29.0 | 29.0
Sprint 47 (Nov 04–Nov 17) | CR32:66 | 66 | 15.0 | 26.0 | 25.0
Sprint 48 (Nov 18–Dec 01) | CR32:20; CR6:40 | 60 | 14.0 | 23.0 | 23.0
Sprint 49 (Dec 02–Dec 15) | CR6:76 | 76 | 18.0 | 29.0 | 29.0

## Slide 5: Sprint Plan (Sprints 50+)
Sprint | Assignments | Total TCs | MJ TCs | Mohammed TCs | Vizarat TCs
Sprint 50 (Dec 16–Dec 29) | CR6:76 | 76 | 18.0 | 29.0 | 29.0
Sprint 51 (Dec 30–Jan 12) | CR6:40; CR24:2; CR25:11; CR29:24; CR11:8; CRGrand Total:1 | 86 | 20.0 | 33.0 | 33.0
Sprint 52 (Jan 13–Jan 26) | CRGrand Total:86 | 86 | 20.0 | 33.0 | 33.0
Sprint 53 (Jan 27–Feb 09) | CRGrand Total:86 | 86 | 20.0 | 33.0 | 33.0
Sprint 54 (Feb 10–Feb 23) | CRGrand Total:86 | 86 | 20.0 | 33.0 | 33.0
Sprint 55 (Feb 24–Mar 09) | CRGrand Total:86 | 86 | 20.0 | 33.0 | 33.0

## Slide 6: Risks, Notes & Next Steps
MJ ~60% allocation, Mohammed & Vizarat ~100%.
Test case creation time factored into every sprint.
Sprint numbering continues from 44 onward.
Adjustments can be made as actual sick days/downtime confirmed.