## Slide 1: Test Case Coverage and Sprint Planning Overview
Prepared for: Management Team
Date: September 2025

## Slide 2: Executive Summary
- Completed CRs (May–August), except CR 9 (in progress)
- Upcoming focus: CR 32, CR 6, CR 24, CR 25, CR 29, CR 11
- Team: MJ (50–70%), Mohammed (100%), Vizarat (100%)
- Constraints: KT sessions, app downtimes, holidays, sick days
- Plan: Gradual ramp-up, not all test cases will finish in 2025

## Slide 3: Completed Work (May–August)
- All CRs completed except CR 9 (~1,071 test cases)
- CR 9 still ongoing but mostly automated
- Provides strong baseline for new CRs

## Slide 4: Sprint 44 (Sep 22 – Oct 3, 2025)
- CR 32 → 20 cases
- CR 6 → 20 cases
- Total: ~40 cases
Focus: Kick-off, KT sessions, environment readiness

## Slide 5: Sprint 45 (Oct 6 – Oct 17, 2025)
- CR 32 → 25 cases
- CR 6 → 25 cases
- Total: ~50 cases
Focus: Continue KT + gradual coverage increase

## Slide 6: Sprint 46 (Oct 20 – Oct 31, 2025)
- CR 32 → 30 cases
- CR 24 → 20 cases
- Total: ~50 cases

## Slide 7: Sprint 47 (Nov 3 – Nov 14, 2025)
- CR 25 → 30 cases
- CR 32 → 20 cases
- Total: ~50 cases

## Slide 8: Sprint 48 (Nov 17 – Nov 28, 2025)
- CR 25 → 40 cases
- CR 29 → 10 cases
- Total: ~50 cases

## Slide 9: Sprint 49 (Dec 1 – Dec 12, 2025)
- CR 25 → 40 cases
- CR 11 → 10 cases
- Total: ~50 cases

## Slide 10: Sprint 50 (Dec 15 – Dec 26, 2025, Holiday Sprint)
- CR 25 cleanup → 20 cases
- KT / Documentation focus
- Total: ~20 cases
Limited productivity due to holidays

## Slide 11: Sprint 51 (Jan 5 – Jan 16, 2026)
- CR 25 remainder → 40 cases
- Additional CRs if ready
- Total: ~40–50 cases

## Slide 12: Sprint 52 (Jan 19 – Jan 30, 2026)
- CR 25 final wrap-up → 30 cases
- Begin new CRs as prioritized
- Total: ~40–50 cases

## Slide 13: 2026 Outlook
- Remaining CR 25 completed by Jan 2026
- New CRs prioritized after backlog reduction
- Ramp-up to ~80–100 cases per sprint expected in Q1 2026
- Increased efficiency after KT completion

## Slide 14: Risks & Assumptions
Risks:
- CR 9 spillover may impact new CRs
- App downtimes, holidays, sick days reduce coverage
- Learning curve for new CRs slows execution
Assumptions:
- KT sessions fixed at 30 mins/day
- Realistic ramp-up in 2026
- Team size remains constant

## Slide 15: Q&A
Questions & Discussion
Thank you!